# SHARP EV AI Chatbot

## Project Effort Estimation

Prepared by: Solution Architect   |   Date: 2026-06-22   |   Version: 1.0   |   Unit: Person-Weeks (PW)  ·  1 PW = 5 Person-Days

| SA Solution Architect 1 person | AIL AI Lead 1 person | AIE AI Engineer 2 persons | QA QA Engineer 1 person | Total Team 5 persons |
| --- | --- | --- | --- | --- |

# 1.  Effort Summary by Phase

| Phase | Cal. Weeks | SA (PW) | AI Lead (PW) | AIE 1 (PW) | AIE 2 (PW) | QA (PW) | Phase Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — Discovery & Architecture | 2 | 2.0 | 2.0 | 1.0 | 1.0 | 1.0 | 7.0 |
| Phase 2 — Infrastructure & Env Setup | 2 | 2.0 | 1.0 | 1.5 | 1.5 | 1.0 | 7.0 |
| Phase 3A — Self-Diagnosis Module | 4 | 0.5 | 3.0 | 3.0 | 1.5 | 2.0 | 10.0 |
| Phase 3B — EV Usage Consultation (RAG) | 5 | 0.5 | 4.5 | 3.5 | 2.0 | 2.5 | 13.0 |
| Phase 3C — General Chat | 2 | 0.0 | 1.0 | 0.5 | 1.5 | 0.5 | 3.5 |
| Phase 3D — General Automotive Guidance | 2 | 0.0 | 1.0 | 1.5 | 0.5 | 1.0 | 4.0 |
| Phase 4 — Voice I/O & Security | 2 | 1.5 | 1.0 | 1.5 | 1.5 | 1.0 | 6.5 |
| Phase 5 — Integration Testing & UAT | 3 | 1.0 | 2.5 | 2.0 | 2.0 | 4.5 | 12.0 |
| Phase 6 — Production Deployment | 2 | 1.5 | 1.0 | 0.5 | 1.5 | 2.5 | 7.0 |
| TOTAL PERSON-WEEKS | 24 wks | 9.0 PW (45 days) | 17.0 PW (85 days) | 15.0 PW (75 days) | 13.0 PW (65 days) | 16.0 PW (80 days) | 70.0 PW (350 days) |

# 2.  Project Timeline  (16 Weeks / ~4 Months)

| Phase / Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Discovery & Architecture | ▮ | ▮ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2: Infrastructure Setup |  |  | ▮ | ▮ |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 3A: Self-Diagnosis Module |  |  |  |  | ▮ | ▮ | ▮ | ▮ |  |  |  |  |  |  |  |  |
| Phase 3B: EV Usage Consult (RAG) |  |  |  |  | ▮ | ▮ | ▮ | ▮ | ▮ |  |  |  |  |  |  |  |
| Phase 3C: General Chat |  |  |  |  |  | ▮ | ▮ |  |  |  |  |  |  |  |  |  |
| Phase 3D: General Auto Guidance |  |  |  |  |  |  | ▮ | ▮ |  |  |  |  |  |  |  |  |
| Phase 4: Voice I/O & Security |  |  |  |  |  |  |  | ▮ | ▮ |  |  |  |  |  |  |  |
| Phase 5: Integration Testing & UAT |  |  |  |  |  |  |  |  |  | ▮ | ▮ | ▮ |  |  |  |  |
| Phase 6: Production Deployment |  |  |  |  |  |  |  |  |  |  |  |  | ▮ | ▮ | ▮ | ▮ |

# 3.  Phase-by-Phase Activity Breakdown

Phase 1 — Discovery & Architecture · Week 1–2

SA (2 PW)

▸ Requirements workshops with SHARP client

▸ AWS architecture design (HLD + LLD)

▸ Multi-modal RAG design review

▸ Cloud account setup + IAM strategy

AI Lead (2 PW)

▸ AI/ML stack selection (Bedrock, SageMaker, Kendra)

▸ Multi-modal RAG architecture design

▸ Embedding model selection (Titan v2 + Multimodal)

▸ LLM evaluation framework design

AIE 1 (1 PW)

▸ Research spike: Bedrock + RAG patterns

▸ Vehicle telemetry API feasibility check

AIE 2 (1 PW)

▸ Research spike: COCORO MEMBERS ID OAuth flow

▸ API Gateway + Lambda architecture spike

QA (1 PW)

▸ Test strategy document

▸ Test environment requirements

▸ Acceptance criteria definition

Phase 2 — Infrastructure & Environment Setup · Week 3–4

SA (2 PW)

▸ VPC, subnets, security groups, IAM roles

▸ CI/CD pipeline (CodePipeline + CodeBuild)

▸ CloudWatch dashboards + alerting baseline

▸ WAF + Shield baseline setup

AI Lead (1 PW)

▸ Amazon Bedrock model access + quota requests

▸ OpenSearch Serverless cluster provisioning

▸ SageMaker Studio workspace setup

AIE 1 (1.5 PW)

▸ AWS IoT Core + Kinesis stream setup

▸ Lambda project scaffold + deployment framework

▸ S3 buckets + lifecycle policies

AIE 2 (1.5 PW)

▸ API Gateway + Lambda scaffold

▸ Amazon Cognito + COCORO MEMBERS ID integration

▸ DynamoDB tables (sessions, conversation history)

QA (1 PW)

▸ Test environment provisioned (dev / staging)

▸ Test data preparation (mock vehicle telemetry)

▸ Postman / test automation framework setup

Phase 3A — Self-Diagnosis Module · Week 5–8

SA (0.5 PW)

▸ Architecture review — vehicle data flow

▸ Security sign-off for vehicle telemetry pipeline

AI Lead (3 PW)

▸ SageMaker fault diagnosis ML model training + tuning

▸ Amazon Rekognition integration (warning light image analysis)

▸ Diagnosis confidence scoring logic

▸ Severity classification (Critical / Warning / Info)

AIE 1 (3 PW)

▸ IoT Core → Kinesis → Lambda pipeline build

▸ Fault code database (Aurora) schema + ingestion

▸ Step Functions diagnosis workflow orchestration

▸ Vehicle image upload (S3) + Rekognition trigger

AIE 2 (1.5 PW)

▸ Diagnosis API (REST) — request/response contract

▸ Dealer booking integration stub

▸ Diagnosis history storage (DynamoDB + Aurora)

QA (2 PW)

▸ Test cases: 50+ fault scenarios (OBD-II codes)

▸ Image recognition accuracy tests (warning lights)

▸ End-to-end diagnosis flow testing

▸ Severity classification validation

Phase 3B — EV Usage Consultation (Multi-modal RAG) · Week 5–9

SA (0.5 PW)

▸ Data residency review — manual storage compliance

▸ RAG architecture sign-off

AI Lead (4.5 PW)

▸ Document ingestion pipeline design + orchestration

▸ Amazon Textract — PDF OCR + table extraction

▸ Titan Text Embeddings v2 — chunk generation

▸ Titan Multimodal Embeddings — vehicle diagram indexing

▸ Amazon Kendra index setup + manual ingestion

▸ Cohere Rerank v3 integration for re-scoring

▸ Prompt augmentation templates per module

▸ RAG accuracy tuning (recall / precision)

AIE 1 (3.5 PW)

▸ Document loader Lambda (PDF → chunks → embeddings)

▸ OpenSearch kNN index build + mapping configuration

▸ Chunk metadata store (DynamoDB)

▸ Index refresh pipeline (new manual versions)

AIE 2 (2 PW)

▸ Retrieval API — query → embed → kNN → rerank

▸ Response formatter — answer + page citation + URL

▸ Fallback handler (no-answer / low-confidence)

QA (2.5 PW)

▸ RAG accuracy benchmark testing (over XX% target)

▸ Citation accuracy — correct page references

▸ Multi-model (text + image query) testing

▸ Fallback response quality validation

Phase 3C — General Chat · Week 6–7

AI Lead (1 PW)

▸ Bedrock Claude 3 system prompt design

▸ Guardrails configuration (topic scoping)

▸ Content moderation rules (METI compliance)

AIE 1 (0.5 PW)

▸ Chat session API integration support

AIE 2 (1.5 PW)

▸ Chat session API — WebSocket + REST

▸ Multi-turn conversation history (DynamoDB)

▸ Usage limit enforcement (XX req/month quota)

QA (0.5 PW)

▸ Conversation flow testing (multi-turn)

▸ Guardrail effectiveness testing

Phase 3D — General Automotive Guidance · Week 7–8

AI Lead (1 PW)

▸ Automotive knowledge base ingestion + indexing

▸ Domain-specific RAG prompt tuning

▸ Cohere multilingual embed for JP/EN content

AIE 1 (1.5 PW)

▸ KB document loader + chunking pipeline

▸ OpenSearch automotive index + metadata schema

AIE 2 (0.5 PW)

▸ Automotive guidance API + response formatter

QA (1 PW)

▸ Automotive guidance accuracy testing

▸ Cross-module boundary testing (chat vs auto)

Phase 4 — Voice I/O & Security · Week 8–9

SA (1.5 PW)

▸ AWS WAF rules (geo-block, rate limit, SQLi)

▸ AWS Shield Advanced activation

▸ Amazon GuardDuty threat detection config

▸ Security architecture review + pen test scope

AI Lead (1 PW)

▸ Amazon Transcribe — Japanese STT model tuning

▸ Amazon Polly — TTS voice character selection + testing

AIE 1 (1.5 PW)

▸ Transcribe streaming API integration

▸ Voice session auto-deactivation timer (TBD value)

▸ STT accuracy validation pipeline

AIE 2 (1.5 PW)

▸ Polly TTS integration — text → voice response

▸ Voice + text parallel response delivery

▸ Rate limiter Lambda (XX req/month enforcement)

QA (1 PW)

▸ STT accuracy testing (over XX% target)

▸ TTS quality review (voice + transcript sync)

▸ Security scan (OWASP, replay attack tests)

Phase 5 — Integration Testing & UAT · Week 10–12

SA (1 PW)

▸ End-to-end architecture validation

▸ Performance & load test review

▸ UAT environment sign-off

AI Lead (2.5 PW)

▸ Full RAG pipeline accuracy benchmark (all 4 modules)

▸ LLM response quality review + prompt tuning

▸ UAT support — AI-related defect triage

AIE 1 (2 PW)

▸ End-to-end integration — cross-module testing

▸ Bug fixes — ingestion + retrieval pipeline

▸ Performance profiling + bottleneck resolution

AIE 2 (2 PW)

▸ Bug fixes — API, auth, voice, usage limits

▸ Cross-browser / cross-device compatibility

▸ Load testing support

QA (4.5 PW)

▸ Full regression test suite execution

▸ Performance testing (concurrent users load test)

▸ Security penetration testing

▸ UAT facilitation with SHARP stakeholders

▸ Defect management + retesting

Phase 6 — Production Deployment & Handover · Week 13–16

SA (1.5 PW)

▸ Production deployment runbook

▸ CloudWatch production dashboards + alarms

▸ Cost optimisation review (LLM API + infra)

▸ Architecture handover documentation

AI Lead (1 PW)

▸ Production model deployment + smoke test

▸ RAG accuracy production validation

▸ AI runbook + model retraining guide

AIE 1 (0.5 PW)

▸ Production deployment + rollback support

AIE 2 (1.5 PW)

▸ Production deployment + smoke testing

▸ Monitoring dashboards handover

QA (2.5 PW)

▸ Production smoke + sanity testing

▸ Go/No-Go sign-off checklist

▸ Test evidence pack for METI compliance

# 4.  Total Effort Summary

| Role | Count | Total PW | Total Days | Availability | Notes |
| --- | --- | --- | --- | --- | --- |
| Solution Architect | 1 | 9.0 PW | 45 days | 45 | Part-time from Phase 3 onwards |
| AI Lead | 1 | 17.0 PW | 85 days | 85 | Full-time — critical path owner |
| AI Engineer 1 | 1 | 15.0 PW | 75 days | N/A | Full-time — pipeline & IoT specialist |
| AI Engineer 2 | 1 | 13.0 PW | 65 days | N/A | Full-time — API & auth specialist |
| QA Engineer | 1 | 16.0 PW | 80 days | N/A | Full-time from Phase 2 onwards |
| GRAND TOTAL | 5 | 70.0 PW | 350 days | 16 Weeks | Project Duration: ~4 Months |

# 5.  Key Assumptions

Scope

All 4 modules (Self-diagnosis, EV Usage Consultation, Chat, General Auto Guidance) are in scope for v1.

Voice I/O (Japanese STT + TTS) is included in v1.

COCORO MEMBERS ID auth integration is in scope; SSO API spec provided by SHARP.

Client Inputs

SHARP provides EV manuals in digital format (PDF/HTML) within Week 1.

Vehicle telemetry API spec / sandbox provided by Week 2.

All TBD values (accuracy %, response time, concurrent users, usage cap) confirmed in Phase 1.

SHARP assigns a technical point-of-contact for weekly progress reviews.

Technology

Amazon Bedrock (Claude 3 Sonnet/Haiku) access approved and quota granted before Phase 3.

No custom LLM fine-tuning required — prompt engineering and RAG are sufficient.

AWS region: ap-northeast-1 (Tokyo) for data residency compliance.

Existing AWS account provided by SHARP or new account created in Phase 1.

Team

All 5 team members are available full-time from project start.

2 AI Engineers have prior experience with AWS Lambda, API Gateway, and Python.

AI Lead has hands-on experience with RAG pipelines and Amazon Bedrock.

No team ramp-up time required beyond the Phase 1 research spike.

Excluded

Mobile app (iOS/Android) UI development — assumed to be handled by SHARP or a separate team.

In-car head unit integration — out of scope for v1.

Custom LLM training or fine-tuning.

Dealer booking system integration (stub API only in v1).

Multi-region deployment — Japan (ap-northeast-1) only for v1.

# 6.  Key Risks

| Level | Risk | Mitigation | Impacted Phase |
| --- | --- | --- | --- |
| HIGH | TBD values not confirmed by SHARP in Phase 1 (accuracy %, response time, concurrent users). | Resolve all XX placeholders in Phase 1 workshops. Block Phase 3 start if unresolved. | Phase 1 |
| HIGH | Vehicle telemetry API does not exist — needs to be built by SHARP. | Phase 3A (Self-diagnosis) is gated on this API. Add 3–4 PW buffer if SHARP needs to build it. | Phase 3A |
| HIGH | EV manuals provided as scanned PDFs — OCR quality degrades RAG accuracy. | Demand machine-readable source in Phase 1. If scanned only, add 2 PW for Textract QA. | Phase 3B |
| MEDIUM | Amazon Bedrock Claude 3 quota limits delay LLM integration. | Request quota increase in Week 1. Maintain fallback to Claude 2 or GPT-4 via API Gateway. | Phase 3 start |
| MEDIUM | COCORO MEMBERS ID OAuth spec delayed or incomplete. | Use mock auth in dev environment. Block production UAT until full spec received. | Phase 4–5 |
| MEDIUM | Japanese STT (Transcribe) accuracy below target for automotive vocabulary. | Add custom vocabulary list in Phase 4. Budget 1 additional PW for AIL tuning. | Phase 4 |
| LOW | OpenSearch kNN search latency exceeds response time target. | Add ElastiCache semantic cache layer (planned). Optimise top-K value and shard count. | Phase 5 |
| LOW | METI AI compliance requirements more stringent than expected. | Schedule legal review in Phase 1. Add 1 PW SA + 1 PW QA buffer for compliance evidence. | Phase 1 |

Total Effort: 70.0 Person-Weeks  (350 Person-Days)   |   Project Duration: 16 Weeks (~4 Months)   |   Team: 5 members   |   SHARP EV AI Chatbot — Confidential